## How to use
How to use this Gantt chart
1. Each Friday, fill in the yellow cells on the Gantt sheet: actual start, actual end and % complete for anything you worked on.
2. Typing 100% in % complete ticks the task off (✓) and colours its status green.
3. Status updates by itself from today's date: Not started, On track, Behind (less done than the time used suggests), Late (past the planned end), Done.
4. If a task slips, change its Planned start and end, write the reason in Notes, and add a row to the Change log. Never edit the Baseline columns: they are the original plan the mid-term review compares against.
5. Slip vs baseline shows, in weeks, how far each task has moved from the original plan (red when late).
6. Critical tasks (red bars) have no float: if one slips, the tasks after it slip too. Non-critical tasks (grey) can use their float (hatched) without delaying the project.
7. ● marks the weeks you actually worked on a task (from Actual start to Actual end, or to today if it is still running). ◆ marks a milestone.
8. Week 1 starts on Monday 19 October 2026. Assessment dates (mid-term, report, demonstration) are planned dates: confirm them on Blackboard under Assessment Feedback and update the milestones.
9. For the mid-term review, print or screenshot the Gantt sheet with the Change log: together they are the original and revised plan the handbook asks for.

## Gantt
EE3EPJ Project Gantt Chart: AdaptEnergy (Adaptive Closed-Loop Home Energy Controller)
Oluwatomisin Agbaje · 240369394 · Supervisors: Dr Faisal M Shah, Dr Andrew Cross · baseline agreed 23 Oct 2026
| Week 1 starts (Monday) |  | 2026-10-19 |  |  | Current week |  | 1 |  | Tasks behind or late |  |  | 6
| Today |  | 2026-10-23 |  |  | Overall progress |  | 0% |  | Milestones done |  |  | 1 of 14
Week number (top) and Monday date (below). ● = actual work, ◆ = milestone
ID | Task | Type | Objective | Depends on | Critical? | Baseline start | Baseline end | Planned start | Planned end | Duration (wks) | Float (wks) | Actual start | Actual end | % complete | Status | Slip vs baseline (wks) | Done | Earned (wks) | Notes / reason for change | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
[20 empty] | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24
| Project management | Group
PM1 | Proposal review | Milestone |  |  | Yes | 2026-10-21 | 2026-10-21 | 2026-10-21 | 2026-10-21 |  |  |  | 2026-10-21 |  | Done | 0 | ✓ |  | Held 21 Oct 2026; mark 46.9%; feedback built into the v5 deck and this plan | bar: 2026-10-19
PM2 | Confirm Blackboard tasks (ethics, H&S, codes, inclusion) signed and uploaded | Task |  |  | Yes | 2026-10-26 | 2026-10-30 | 2026-10-26 | 2026-10-30 | 1 | 0 |  |  |  | Not started | 0 |  | 0
PM3 | Set up hardback logbook; first signed entry | Task |  |  | No | 2026-10-26 | 2026-10-30 | 2026-10-19 | 2026-10-30 | 2 | 0 |  |  |  | Behind | 0 |  | 0
PM4 | Technical risk register v1 (review every fortnight after) | Task |  |  | No | 2026-10-26 | 2026-10-30 | 2026-10-19 | 2026-10-30 | 2 | 1 |  |  |  | Behind | 0 |  | 0
PM5 | Supervisor meetings, fortnightly, with minutes (term 1) | Task |  |  | No | 2026-10-19 | 2026-12-18 | 2026-10-19 | 2026-12-18 | 9 | 0 |  |  |  | On track | 0 |  | 0
PM6 | Supervisor meetings, weekly, with minutes (term 2) | Task |  |  | No | 2027-01-25 | 2027-04-23 | 2027-01-25 | 2027-04-23 | 13 | 0 |  |  |  | Not started | 0 |  | 0
PM7 | Mid-term pack: deck, logbook, literature review, original and revised Gantt | Task |  | F3 | Yes | 2027-02-15 | 2027-02-19 | 2027-02-08 | 2027-02-19 | 2 | 0 |  |  |  | Not started | 0 |  | 0
PM8 | Mid-term review (confirm date on Blackboard) | Milestone |  | PM7 | Yes | 2027-02-22 | 2027-02-22 | 2027-02-22 | 2027-02-22 | [5 empty] | Upcoming | 0 | bar: 2027-02-22
| Literature review | Group
L1 | Literature search: 15 sources logged | Task |  |  | No | 2026-10-19 | 2026-11-06 | 2026-10-19 | 2026-10-30 | 2 | 2 |  |  |  | Behind | -1 |  | 0
L2 | Literature comparison table and gap (30 sources) | Task |  | L1 | No | 2026-11-09 | 2026-11-27 | 2026-11-02 | 2026-11-13 | 2 | 2 |  |  |  | Not started | -2 |  | 0
L3 | Literature review chapter drafted | Task |  | L2 | No | 2026-11-30 | 2026-12-18 | 2026-11-16 | 2026-11-27 | 2 | 0 |  |  |  | Not started | -3 |  | 0
L4 | Literature review draft sent to Dr Shah | Milestone |  | L3 | No | 2026-12-18 | 2026-12-18 | 2026-11-27 | 2026-11-27 | [5 empty] | Upcoming | -3 | bar: 2026-11-23
| Data and software (laptop) | Group
S1 | Download and store a year of Octopus and Elexon data | Task | O1 |  | No | 2026-10-26 | 2026-10-30 | 2026-10-19 | 2026-10-30 | 2 | 1 |  |  |  | Behind | 0 |  | 0
S2 | Data pipeline: cleaning and alignment | Task | O1 | S1 | No | 2026-11-02 | 2026-11-20 | 2026-10-26 | 2026-11-06 | 2 | 1 |  |  |  | Not started | -2 |  | 0
S3 | O1 met: T1 data-quality report | Milestone | O1 | S2 | No | 2026-11-20 | 2026-11-20 | 2026-11-06 | 2026-11-06 | [5 empty] | Upcoming | -2 | bar: 2026-11-02
S4 | Python simulator skeleton | Task | O8 | S2 | No | 2026-11-23 | 2026-11-27 | 2026-11-02 | 2026-11-06 | 1 | 2 |  |  |  | Not started | -3 |  | 0
S5 | Perfect plan by linear programming | Task | O8 | S4 | No | 2026-11-30 | 2026-12-04 | 2026-11-09 | 2026-11-13 | 1 | 2 |  |  |  | Not started | -3 |  | 0
S6 | DP state count and timing in Python | Task | O6 | S4 | No | 2026-12-07 | 2026-12-11 | 2026-11-09 | 2026-11-13 | 1 | 1 |  |  |  | Not started | -4 |  | 0
S7 | Baseline forecasters and first results | Task | O5 | S2 | No | 2026-12-14 | 2026-12-18 | 2026-11-16 | 2026-11-20 | 1 | 5 |  |  |  | Not started | -4 |  | 0
S8 | LightGBM forecaster against baselines (T5) | Task | O5 | S7 | No | 2027-01-25 | 2027-01-29 | 2026-11-23 | 2026-12-04 | 2 | 1 |  |  |  | Not started | -8 |  | 0
S9 | O5 met: forecaster results | Milestone | O5 | S8 | No | 2027-01-29 | 2027-01-29 | 2026-12-04 | 2026-12-04 | [5 empty] | Upcoming | -8 | bar: 2026-11-30
| Hardware | Group
H1 | Order chips and parts via technician (by Wed 28 Oct, 17:00) | Task |  |  | Yes | 2026-10-19 | 2026-10-30 | 2026-10-19 | 2026-10-30 | 2 | 0 |  |  |  | Behind | 0 |  | 0
H2 | Proteus practice task | Task |  |  | No | 2026-10-26 | 2026-10-30 | 2026-10-19 | 2026-10-30 | 2 | 1 |  |  |  | Behind | 0 |  | 0
H3 | Sensing PCB: schematic in Proteus, technician review | Task | O2 | H1 | Yes | 2026-11-02 | 2026-11-06 | 2026-10-26 | 2026-10-30 | 1 | 0 |  |  |  | Not started | -1 |  | 0
H4 | Sensing PCB: layout, design-rule check, Tuesday submission | Task | O2 | H3 | Yes | 2026-11-09 | 2026-11-13 | 2026-11-02 | 2026-11-06 | 1 | 0 |  |  |  | Not started | -1 |  | 0
H5 | Sensing PCB: assembly on the SMD station | Task | O2 | H4 | Yes | 2026-11-16 | 2026-11-20 | 2026-11-09 | 2026-11-13 | 1 | 0 |  |  |  | Not started | -1 |  | 0
H6 | Sensing PCB: T2 calibration sweep | Task | O2 | H5 | Yes | 2026-11-23 | 2026-11-27 | 2026-11-09 | 2026-11-13 | 1 | 0 |  |  |  | Not started | -2 |  | 0
H7 | O2 met: sensing PCB | Milestone | O2 | H6 | Yes | 2026-11-27 | 2026-11-27 | 2026-11-13 | 2026-11-13 | [5 empty] | Upcoming | -2 | bar: 2026-11-09
H8 | Over-current trip on breadboard; switching schematic | Task | O4 | H1 | No | 2026-11-16 | 2026-11-20 | 2026-11-02 | 2026-11-13 | 2 | 1 |  |  |  | Not started | -1 |  | 0
H9 | Switching PCB: layout and submission | Task | O4 | H8 | No | 2026-11-23 | 2026-11-27 | 2026-11-09 | 2026-11-13 | 1 | 1 |  |  |  | Not started | -2 |  | 0
H10 | Switching PCB: assembly | Task | O4 | H9 | No | 2026-11-30 | 2026-12-04 | 2026-11-16 | 2026-11-20 | 1 | 1 |  |  |  | Not started | -2 |  | 0
H11 | Switching PCB: T4 tests | Task | O4 | H10 | No | 2026-12-07 | 2026-12-11 | 2026-11-16 | 2026-11-20 | 1 | 1 |  |  |  | Not started | -3 |  | 0
H12 | O4 met: switching and protection PCB | Milestone | O4 | H11 | No | 2026-12-11 | 2026-12-11 | 2026-11-20 | 2026-11-20 | [5 empty] | Upcoming | -3 | bar: 2026-11-16
H13 | Electronic load: breadboard loop, step response, tuning | Task | O3 | H6 | Yes | 2026-11-30 | 2026-12-04 | 2026-11-16 | 2026-11-20 | 1 | 0 |  |  |  | Not started | -2 |  | 0
H14 | Electronic load: PCB submission | Task | O3 | H13 | Yes | 2026-12-07 | 2026-12-11 | 2026-11-23 | 2026-11-27 | 1 | 0 |  |  |  | Not started | -2 |  | 0
H15 | Electronic load: assembly and T3 tests | Task | O3 | H14 | Yes | 2026-12-14 | 2026-12-18 | 2026-11-23 | 2026-12-04 | 2 | 0 |  |  |  | Not started | -2 |  | 0
H16 | O3 met: electronic load | Milestone | O3 | H15 | Yes | 2026-12-18 | 2026-12-18 | 2026-12-04 | 2026-12-04 | [5 empty] | Upcoming | -2 | bar: 2026-11-30
H17 | Battery round-trip efficiency test | Task | O8 | H1 | No | 2026-12-07 | 2026-12-11 | 2026-11-23 | 2026-11-27 | 1 | 1 |  |  |  | Not started | -2 |  | 0
| Christmas and January exams | Group
X1 | Christmas and January exams (no planned project work) | Break |  |  |  | 2026-12-21 | 2027-01-22 | 2026-12-21 | 2027-01-22
| Firmware and interface (ESP32) | Group
F1 | FreeRTOS practice task | Task | O6 |  | No | 2026-11-02 | 2026-11-06 | 2026-10-26 | 2026-11-06 | 2 | 2 |  |  |  | Not started | 0 |  | 0
F2 | DP planner on the ESP32 under FreeRTOS | Task | O6 | H15, S6 | Yes | 2027-01-25 | 2027-02-12 | 2026-12-07 | 2027-01-29 | 8 | 0 |  |  |  | Not started | -2 |  | 0
F3 | T6: re-plan timing and memory | Task | O6 | F2 | Yes | 2027-02-15 | 2027-02-19 | 2027-01-25 | 2027-01-29 | 1 | 0 |  |  |  | Not started | -3 |  | 0
F4 | O6 met: adaptive controller | Milestone | O6 | F3 | Yes | 2027-02-26 | 2027-02-26 | 2027-01-29 | 2027-01-29 | [5 empty] | Upcoming | -4 | bar: 2027-01-25
U1 | LCD, LED price bar and buttons | Task | O7 | H11 | No | 2027-01-25 | 2027-02-05 | 2026-12-07 | 2026-12-18 | 2 | 1 |  |  |  | Not started | -7 |  | 0
U2 | MQTT dashboard (Mosquitto, SQLite, Streamlit) | Task | O7 | U1 | No | 2027-02-08 | 2027-02-19 | 2027-01-25 | 2027-02-05 | 2 | 1 |  |  |  | Not started | -2 |  | 0
U3 | T7: display and IoT tests | Task | O7 | U2 | No | 2027-02-22 | 2027-02-26 | 2027-02-01 | 2027-02-05 | 1 | 1 |  |  |  | Not started | -3 |  | 0
U4 | O7 met: display and IoT | Milestone | O7 | U3 | No | 2027-03-05 | 2027-03-05 | 2027-02-05 | 2027-02-05 | [5 empty] | Upcoming | -4 | bar: 2027-02-01
| Integration and evaluation | Group
I1 | Integration: all boards, ESP32 and laptop in one loop | Task | O8 | F3 | Yes | 2027-02-22 | 2027-03-05 | 2027-02-01 | 2027-02-12 | 2 | 0 |  |  |  | Not started | -3 |  | 0
E1 | Simulation: five scenarios over the held-out year | Task | O8 | I1, S5 | Yes | 2027-03-08 | 2027-03-19 | 2027-01-25 | 2027-02-05 | 2 | 0 |  |  |  | Not started | -6 |  | 0
E2 | Rig runs: 24 replayed days | Task | O8 | I1 | Yes | 2027-03-15 | 2027-03-26 | 2027-02-08 | 2027-02-19 | 2 | 0 |  |  |  | Not started | -5 |  | 0
E3 | Trade-off studies (shunt, emulation, resolution, re-plan rate, forecast value) | Task | O8 | I1 | No | 2027-03-08 | 2027-03-26 | 2027-02-01 | 2027-02-19 | 3 | 1 |  |  |  | Not started | -5 |  | 0
E4 | Statistics and T8 | Task | O8 | E1, E2 | Yes | 2027-03-22 | 2027-03-26 | 2027-02-15 | 2027-02-19 | 1 | 0 |  |  |  | Not started | -5 |  | 0
E5 | O8 met: evaluation | Milestone | O8 | E4 | Yes | 2027-03-26 | 2027-03-26 | 2027-02-19 | 2027-02-19 | [5 empty] | Upcoming | -5 | bar: 2027-02-15
E6 | Extensions, only if on track | Task |  | I1 | No | 2027-03-08 | 2027-04-02 | 2027-02-22 | 2027-03-19 | 4 | 0 |  |  |  | Not started | -2 |  | 0
| Report and demonstration | Group
W1 | Report: Chapters 1 and 3 drafted | Task |  |  | No | 2026-11-02 | 2026-12-18 | 2026-10-26 | 2026-11-27 | 5 | 2 |  |  |  | Not started | -3 |  | 0
W2 | Report: design and implementation chapters | Task |  | I1 | No | 2027-03-01 | 2027-03-05 | 2027-02-01 | 2027-02-12 | 2 | 1 |  |  |  | Not started | -3 |  | 0
W3 | Report: testing chapter | Task |  | E2 | No | 2027-03-15 | 2027-03-19 | 2027-02-15 | 2027-02-19 | 1 | 1 |  |  |  | Not started | -4 |  | 0
W4 | Report: evaluation and reflection chapters | Task |  | E4 | Yes | 2027-03-22 | 2027-04-02 | 2027-02-22 | 2027-02-26 | 1 | 0 |  |  |  | Not started | -5 |  | 0
W5 | Full report draft to Dr Shah | Milestone |  | W4 | Yes | 2027-03-29 | 2027-03-29 | 2027-03-01 | 2027-03-01 | [5 empty] | Upcoming | -4 | bar: 2027-03-01
W6 | Revise from feedback; references, figures, word count, code annexe | Task |  | W5 | Yes | 2027-04-05 | 2027-04-23 | 2027-03-01 | 2027-03-19 | 3 | 0 |  |  |  | Not started | -5 |  | 0
W7 | Report submitted (confirm date on Blackboard) | Milestone |  | W6 | Yes | 2027-04-23 | 2027-04-23 | 2027-03-26 | 2027-03-26 | [5 empty] | Upcoming | -4 | bar: 2027-03-22
D1 | Demonstration: rehearsal, recorded backup, results poster | Task |  | W7 | Yes | 2027-04-26 | 2027-05-07 | 2027-03-29 | 2027-05-07 | 6 | 0 |  |  |  | Not started | 0 |  | 0
D2 | Demonstration (confirm date on Blackboard) | Milestone |  | D1 | Yes | 2027-05-10 | 2027-05-10 | 2027-05-10 | 2027-05-10 | [5 empty] | Upcoming | 0 | bar: 2027-05-10
Legend
Critical path (any slip delays the project)
Non-critical task
Float (slack): can slip this far without delaying anything
Christmas and exams (no project work)
Current week
● | Actual work: drawn from your actual start date to your actual end date (or today)
◆ | Milestone (the date in Planned start/end)
Yellow cells are yours to fill in; everything else updates by itself
Baseline = the official plan (never edit). Planned = my ahead-of-schedule targets (aim: O8 done 5 weeks early). Negative slip = weeks ahead.
Note on B6: Edit the yellow cells only: planned dates when you re-plan, actual start and end, % complete and notes. Baseline dates stay frozen for the mid-term review.

## Change log
Change log: every slip or re-plan, for the mid-term review
The handbook asks for the original and revised plan, with slippages and how changes were decided. Add a row each time you move a planned date.
Date | Task ID | Task | Old planned end | New planned end | Slip (days) | Reason | Decision and who agreed it | Logbook page
2026-10-23 | PM1 | Proposal review | 2026-10-21 | 2026-10-21 | 0 | Example row: no change, proposal review held as planned | None needed